## Version Control
Version # | Implemented | Revision | Approved | Approval | Reason
| By | Date | By | Date
1 | Jackson Low | 2021-09-17 | Chan Shao Jing | 2021-09-17 | Initial Risk Management Log Draft
Lionel Wong

## Risk Management Log
No. | Risk Type | Risk Description | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Unable to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delay the deployment date. | Shao Jing | Mitigate | Have regular meetings and updates from the developer team to check on their progress.
2 | Hardware | Hardware failure e.g., Hard Drive corrupted | Low | High |  | 4 | Unable to meet deadlines as codes cannot be written or ran. | Jackson | Mitigate | Maintain backups via version control software, e.g., git to minimize the impact.
3 | Software | Feature creep | Medium | High |  | 7 | Will delay the project and may not be able to meet the set deadlines. | Zachary | Avoid | Maintain traceability between documentation and code to not go beyond the specified requirements.
4 | Communication | Updates to code not communicated to every group member | High | Medium |  | 7 | Overlapping of codes which may lead to errors while running the program, and documentation may be inaccurate. | Lionel | Avoid | Ensure transparency between group members when it comes to updating of work done, which will lead to less miscommunication and conflicting information.
5 | Resource | Staff Unavailability | Medium | Medium |  | 6 | Staff's work will not be completed. | Ankitha | Transfer | Transfer the workload to other staff workers in order to ensure that work is still completed by deadlines.
6 | Software | System not meeting requirements | Low | High |  | 5 | Scheduled releases may be affected as that would lead to more debugging and testing. | Chi Hui | Avoid | Ensure that testing is done early so that the system can be checked against requirements with ample spare time.
7 | Software | Poor code design (e.g. high coupling) | Low | Medium |  | 3 | Modules cannot be separated | Zachary | Avoid | Design a system architecture and class diagram and ensure that it is followed when coding the application.
8 | External | COVID 19 | Low | Medium |  | 2 | Unable to meet up due to restrictions, teammates contracting the virus. | Jackson | Accept | Ensure that we follow safe distancing measures and minimize physical meetings. Project meetings will all be held on Microsoft Teams if restrictions were to be tightened. In the event that a team member contracts the virus, all team members should perform a swab test and the project maanger will delegate the workload of the affected team member accordingly.
9 | Communication | Misunderstanding/Miscommunication of requirements from stakeholders | Low | High |  | 6 | Requires us to redesign our application which delays the project | Shao Jing | Avoid | Establish a clear set of requirements and ensure that it is signed and agreed by both parties beforehand.
10 | External | Sensitive data being leaked/hacked | Low | High |  | 6 | Loss in customer trust and brand reputation | Lionel | Avoid | Encrypt personal information given to the application so that hackers will not be able to access it.
11 | Communication | Incomplete Documentation | Low | Low |  | 2 | May result in miscommunication between team members and may create issues in the future when maintaining the software | Jackson | Avoid | Perform consistent review of existing documentation and create a list of documentation to be maintained. Ensure that version control is in place for each document so that it is easy to track changes and verify information.
12 | Software | Inconsistent Programming Style | Low | Medium |  | 3 | Code will be harder to read and understand and it will be difficult for another person to maintain the software | Lionel | Avoid | Adhere to proper programming style and principles e.g. names, alignment, locality, comments

## Top 10 Risks
No. | Risk Type | Risk | Probability | Impact | Classification | Numerical Rating | Ramifications | Team Member in Charge | Approach | Course of Action
1 | Resource | Unable to meet Project Deadline | Medium | High |  | 8 | Reduced functionalities or delay the deployment date. | Shao Jing | Mitigate | Have regular meetings and updates from the developer team to check on their progress.
2 | Software | Feature creep | Medium | High |  | 7 | Will delay the project and may not be able to meet the set deadlines. | Zachary | Avoid | Maintain traceability between documentation and code to not go beyond the specified requirements.
3 | Communication | Updates to code not communicated to every group member | High | Medium |  | 7 | Overlapping of codes which may lead to errors while running the program, and documentation may be inaccurate. | Lionel | Avoid | Ensure transparency between group members when it comes to updating of work done, which will lead to less miscommunication and conflicting information.
4 | Communication | Misunderstanding/Miscommunication of requirements from stakeholders | Low | High |  | 6 | Requires us to redesign our application which delays the project | Shao Jing | Avoid | Establish a clear set of requirements and ensure that it is signed and agreed by both parties beforehand.
5 | External | Sensitive data being leaked/hacked | Low | High |  | 6 | Loss in customer trust and brand reputation | Lionel | Avoid | Encrypt personal information given to the application so that hackers will not be able to access it.
5 | Resource | Staff Unavailability | Medium | Medium |  | 6 | Staff's work will not be completed. | Ankitha | Transfer | Transfer the workload to other staff workers in order to ensure that work is still completed by deadlines.
7 | Software | System not meeting requirements | Low | High |  | 5 | Scheduled releases may be affected as that would lead to more debugging and testing. | Chi Hui | Avoid | Ensure that testing is done early so that the system can be checked against requirements with ample spare time.
8 | Hardware | Hardware failure e.g., Hard Drive corrupted | Low | High |  | 4 | Unable to meet deadlines as codes cannot be written or ran. | Jackson | Mitigate | Maintain backups via version control software, e.g., git to minimize the impact.
9 | Software | Poor code design (e.g. high coupling) | Low | Medium |  | 3 | Modules cannot be separated | Zachary | Avoid | Design a system architecture and class diagram and ensure that it is followed when coding the application.
10 | Software | Inconsistent Programming Style | Low | Medium |  | 3 | Code will be harder to read and understand and it will be difficult for another person to maintain the software | Lionel | Avoid | Adhere to proper programming style and principles e.g. names, alignment, locality, comments

## Matrix
Impact | High | 1.Hardware failure e.g., Hard Drive corrupted 2. System not meeting requirements 3. Misunderstanding/Miscommunication of requirements from stakeholders 4. Sensitive data being leaked/hacked | 1. Unable to meet Project Deadline 2. Feature creep
| Medium | 1. Poor code design (e.g. high coupling) 2. COVID 19 | 1. Staff Unavailability | 1. Updates to code not communicated to every group member
| Low | 1. Incomplete Documentation | 1. Inconsistent Programming Style
|  | Low | Medium | High
Probability